## Slide 1: Sphere and the Programme Cycle
Notes: Welcome everyone. Ask if they have their Sphere Handbooks ready as they will need them for this session.
Note: Depending on your participant group, Internet availability and bandwidth concerns, you may opt to encourage participants to open their laptops and access the interactive Handbook (https://handbook.spherestandards.org/). This will facilitate quick searching of the Handbook, but note that page references will not be useful in that application, and be aware that open laptops may lead to participants checking emails during the session. Using the interactive Handbook will be most useful in stage 2 of the activity (described on slide 14).

## Slide 2: At the end of this session you will be able to:
Describe the five phases of the programme cycle
Apply Sphere guidance to support humanitarian response at each phase of the cycle
Notes: Explain the learning objectives. Ask if anyone in the group has participated in humanitarian programme cycle training before. If so, ask where and who offered the training.
Explain that this session focuses on key considerations to ensure that projects are managed in adherence to Sphere guidance, rather than the fundamental tools to manage projects (log-frames, gap and Gantt charts, etc.) For most groups, it is understood that participants will already be familiar with their own organisational tools and templates for programme design, control, and reporting. The emphasis in this session should be to provide additional support to all of them, regardless of the tools they are using.
Explain that this session and Sphere’s use of the programme cycle may be slightly different from what they have studied elsewhere – particularly if they have taken the official Inter-Agency Standing Committee (IASC) Programme Cycle Management training. That is a more formal approach tied directly to official protocols and phases of the UN agencies’ programming and budget cycles. This session deals with the basic principles, but does not directly support the IASC Cluster and OCHA-supported training modules on this topic.

## Slide 3: What is the programme cycle?
Assessment and analysis
Strategy development
Planning and programme design
Implementation and monitoring
Evaluation and learning
See page 9
Notes: Show the diagram and ask what it means to participants. If you covered STP sessions 3 and/or 5 earlier in your workshop, then this is a recap, and you could use the animations to check if participants can recall the phases.
Refer participants to page 9 of the Sphere Handbook and ask them to quickly review pages 9 and 10. Ask what the primary message is from this brief discussion of the cycle. (Answer: The standards apply throughout the programme cycle)

## Slide 4: The humanitarian programme cycle
Graphic from www.humanitarianresponse.info
Note: The IASC/OCHA programme cycle diagram and phases are slightly different to those used by Sphere.
Despite these differences, the principles are the same.
Notes: NOTE: This slide is optional. If your training group has many international NGOs or UN representatives, it may be useful to show this to highlight the fact that many of them are already using this, and are familiar with this model rather than the slightly different Sphere humanitarian programme cycle model on the previous slide. Explain that this IASC model relates to the specifics of the UN country teams, budgeting and reporting protocols, and that the Sphere model is a simplified version that presents the basic principles. Note that, in fact, the two models are very similar, and the general principles of the cycle apply to both.
Ask participants if they have seen or used this model of the humanitarian programme cycle. Explain that this commonly cited diagram is the model presented in IASC/OCHA Humanitarian Programme Cycle training. Ask participants if they can quickly spot the differences between the two models before highlighting them with the slide animation.

## Slide 5: Assessment and analysis
Starts the cycle
Continues and improves during the response
Immediate assessment incorporates analysis by using Sphere indicators as a baseline to measure against
Notes: Explain that you will quickly review the meaning of each phase to be sure that the main concepts are clear to everyone. Use the following five slides as a simple presentation to move around each phase of the cycle. The aim is simply to explain the model and a few guiding principles – not to initiate a discussion at this point.
Each of the next few slides presents a mixture of key considerations and specific activities for each step in the cycle. As you quickly review each, ask participants to note the distinction, and to provide examples of activities or tools they are using to complete each step of the cycle.
Note: If you are proceeding to STP session 13 (Sphere, Assessment and Analysis) then inform participants this will be the focus of the next (or a later) session. If not, check the key messages in STP 13 and facilitate a longer discussion around this phase.

## Slide 6: Strategy development
Consider all options – and choose your strategy
Distribute directly or provide cash?
Provide seeds and tools or food?
Tanker water from the river or drill a new well?
Order tents, provide local traditional shelter materials, or pay rent?
Notes: Present the example options listed – or add in your own examples, particularly if there are any that are more appropriate for your training group or location. Explain that strategy development is essentially considering all options and selecting those means that are efficient, promote dignity and capacities, reduce vulnerabilities, and will cause the least harm.

## Slide 7: Planning and programme design
Develop quality programmes using well-established professional norms and practices (Sphere)
Do this together with affected people
Understand vulnerabilities and build on capacities
Notes: Present the points listed. No specific tools or activities are presented in this short overview. Ask participants what tools or approaches they are using in project planning, e.g. project plans, organisational planning templates, work breakdown structures, Gantt charts, and staffing charts.

## Slide 8: Implementation and monitoring
Follow established codes of conduct
Train staff and guard against abuse
Be accountable to people in need – don’t delay and check that things are going according to plan
Be accountable to donors – don’t waste time, money, or resources
Notes: Present the points listed. Take a moment to ask if there are certain norms or protocols that participants’ organisations are following around specific tools or approaches to implementation and monitoring.
Note: If you are proceeding to STP session 14 (Sphere and MEAL) then inform participants this will be the focus of a later session. If not, check the key messages in STP 14 and facilitate a longer discussion around this phase. Note there is a trend for monitoring, evaluation, accountability, and learning (MEAL) to be grouped together, even though monitoring and evaluation often appear in different programme cycle phases. Monitoring must start at the same time as implementation, which is why these should not be split between phases.

## Slide 9: Evaluation and learning
Did the programme give the intended results?
Did the people affected evaluate the programme the same way?
Report on both successes and failures
Use successes to learn and train other people and failures to advocate for change
Notes: Present the points listed. Ask if anyone has done field evaluation work, or has written formal evaluation reports. Ask what lessons they have learned from the exercise.

## Slide 10
Notes: Quickly refer to the cycle once more and ask if there are any questions. Clarify any points until you feel everyone understands the model and the meaning of each phase.

## Slide 11: Programme cycle check-up
You are the triage nurse, and the Sphere Handbook is your stethoscope.
Notes: Announce the exercise, and explain that for the rest of the session, the participants will be “triage nurses” (then “doctors”) diagnosing different scenarios from around the programme cycle to determine if they are in line with Sphere guidance or not.
Distribute the handouts from the file STP 12 Programme Cycle Check-Up Exercise.docx (pages 1–4 double-sided, one copy for each participant). Do not distribute pages 5 and 6 (this is the answer sheet).

## Slide 12: Instructions – Step 1: Triage
1. Read through the 10 scenarios on the handout and diagnose each one as either:
Healthy – everything is fine
Needs further examination – you need to know more to decide
Ill – something is definitely wrong and needs fixing
2. An answer form has also been provided. Use only the first column by writing in one of the options provided above. The “Sphere Doctors” will prescribe the guidance from Sphere in the second part of the exercise.
3. You have 10 minutes to provide answers in column 1 starting now.
Notes: Explain the rules. Be clear that the first task is done individually, and that everyone is expected to answer every question on their own using column 1 of the answer sheet handout.

## Slide 13: Which phase are you checking up?
Group 1: scenarios 1 and 2 – Assessment and analysis
Group 2: scenarios 3 and 4 – Strategy development
Group 3: scenarios 5 and 6 – Planning and programme design
Group 4: scenarios 7 and 8 – Implementation and monitoring
Group 5: scenarios 9 and 10 – Evaluation and learning
Notes: Once everyone has filled out column 1 of the answer sheet, divide participants into five groups. Assign each group one phase of the programme cycle, and ask each group to write the cycle phase title they have been assigned at the top of their flip chart.
Instructions for stage 2 are on the next slide.

## Slide 14: Instructions – Step 2: Prescription
As a group – confer and agree on the assessment of your assigned scenarios: healthy, needs further examination or ill.
You are now the “Sphere Doctors”. Prescribe guidance from Sphere to address whatever is wrong in each of your assigned scenarios.
You have 20 minutes to cite specific Sphere guidance in column 2 of the answer form.
List specific Sphere references on your group flip chart.
Notes: Explain that the five working groups are to review their joint initial findings and agree on a diagnosis, then locate and cite specific references from the Sphere Handbook to guide improvements for each scenario.
They should find two to three points for each scenario (they may cite more if they have time). Ask each group to use only a single flip chart sheet for addressing both of their scenarios.
This is the correct moment to advise the participants to use the interactive Handbook online if you have decided to use it: handbook.spherestandards.org.
When the 20 minutes are up, each group has up to 5 minutes to play back their answers to the whole group.

## Slide 15: Your conclusions?
What insights, if any, did you gain?
What is the significance of the programme cycle to your work?
Which phase(s) of the cycle does Sphere relate to?
Notes: Allow a moment for final reflection and ask if there are any volunteers who would like to share their answer for the first question. Once there are no more responses, go on to the second and third questions. Highlight important key points made – and reinforce with your own such as:
anything that was related as something new, or about which participants had not previously thought;
significance to any specific type of work or role mentioned. For example “I am usually doing emergency response, and I hadn’t considered the necessity to reflect and evaluate” or similar;
Sphere relates to all phases of the programme cycle; and
professional humanitarian response means doing all of the phases in the programme cycle. For example, planning without assessment doesn’t make sense. Implementing without monitoring could be a very wasteful exercise. Choosing the best strategy for humanitarian response in a specific context is key to developing good programmes (put another way – it is no use doing the job right, if you aren’t doing the right job).
Ensure that at least the following two messages are highlighted:
    The programme cycle is an important concept in that it relates all phases of humanitarian response and shows the need to conduct each well to maintain the quality of the overall programme.
    Sphere relates to, and provides guidance for, all phases of the programme cycle

## Slide 16: Key messages
    The programme cycle is an important concept in which each phase must be done well to maintain the quality of the overall programme.
    Sphere relates to, and provides guidance for, all phases of the programme cycle, however they are defined.

## Slide 17
Notes: Thank everyone and challenge them to do the same “check-up” exercise they have done in the classroom today on their next humanitarian response programme.